## Main Strat.
STRATEGIC PLAN
Mission | Accelerate Business Success
Vision | To be the resource for business expertise
GOALS: | Objectives: | target | target | Owner | STATUS | Strategies: | Performance | Linkage to | Outcomes/Updates
|  | date | date |  |  |  | Metrics | Accreditation Std.
Enrich Quality of Services | Develop and deploy eCenter to identify our core services and best-practices | built | completed | Susan & Earl |  | One database within eCenter; currently housed in Center IC. | Client Satisfaction Surveys; New projects; CARs; Tools | #3 - Customer & Stakeholder Focus; #4 - Measurement, Analysis, & Knowledge Management | Current on hold. Information has been uploaded to the development site and reviewed several times; updates and re-deign complete; Training of State Lead Center Staff is scheduled for 03/18/2016
|  | 2015-06-30 | Unknown |  | HOLD
| Develop a process for identifying specialists in the network | Update | completed | Susan |  | One database within eCenter |  | #3 - Customer & Stakeholder Focus; #4 - Measurement, Analysis, & Knowledge Management | Data list has been updated - 01/2016; Once eCenter is live each advisor will have ability to update profile in real time.
|  | 2016-01-31 | 2016-01-31 |  | ON TRACK
| Communicate and implement a list of accountability items | beta test | Quarterly issue | Susan & Committee - Kim, Lissa & Gretchen |  | ongoing - Monthly reports from Center IC and Quarterly Centers Accountability Reports (CARs) |  | #4 - Measurement, Analysis, & Knowledge Management | Committee established the definitions; CARs reports are on full cycle now; FY2015 final report was updated to include key ROI categories. Working on Q1 FY2016 now to release by 03/15/2016.
|  | 05/06;08/02; 11/02/2015 | 2016-03-15 |  | ON GOING
Maximize Economic Impact | Rollout Economic Impact form |  | completed | Susan & Ariana |  | Out for review by all Center Directors; final version to be available for paper, email and electronic submission from client | Jobs Created, | #2 - Strategic Planning; | Form completed; reviewed by directors; set to deploy 10/01/2015; centers
|  |  | 2015-06-30 |  | ON TRACK |  | Sales Increase, Business Starts, Capital Infusion | #3 - Customer & Stakeholder Focus; | not using the new format have been notified during Impact data review Nov 2015. All Impact must have forms attached by 01/01/2016 or rejected.
| Visit 4 key partners and 4 HIC prospects per center annually |  |  | Susan |  | define HIC - in process; request feedback from Center Directors; official Diagnostic Measures to be set for FFY2016 |  | #4 - Measurement, Analysis, & Knowledge Management | Definitions released 11/01/2015
|  | Goal set FY2016 | 2016-09-30 |  | ON TRACK |  |  | Knowledge Management | Goals set in FY2016 contracts; monthly reports to begin 03/31/2016
Strengthen Our Team | Deploy a new professional development system | Define scope | completed | Susan, Domini & CBA Committee |  | CBA to new platform with fully defined on-boarding process, skills assessment and professional development path, | Annual Field Satisfaction Survey | #5 - Workforce Focus: | Committee established on-boarding process; reviewed and updated
|  | 2015-09-30 | 2016-09-30 |  | ON GOING |  | Survey; Statewide Conference; CBA | #6 - Program Delivery & Management | curriculum for CBA; set up Assessment tool and "Pillars" of professional development. Must set new Educational partner and move to eCenter when it goes live.
| Define statewide communication methodologies | Present details | completed | Jim & Susan |  | Review and refine, Adopt and Deploy; specific details for client feedback data. |  | #3 - Customer & Stakeholder Focus | No progress to review methods; Revised Client Satisfaction surveys; reporting Feb 2016.
|  | 2015-08-18 |  |  | ON GOING
Enhance Visibility | 4 Unique stakeholder visits/center/year |  | 4/center/yr. | Jim & Susan |  | Define process and requirements; work with existing activies to build higher visibility | Success stories; | #1 - Leadership & Organizational | Set up tracking mechanism in Center IC; Goals in
|  |  | 2016-09-30 |  | ON TRACK |  | Referrals; | Issues; | place for FY2016; monthly reports to begin 03/21/2016
| Adopt and deploy marketing and branding standards | Adopt | Deploy | Jim |  | Review and refine, Adopt and Deploy | Stakeholder visits | #3 - Customer & Stakeholder Focus | Jim is on track to include with SBDC RFP April 2016.
|  | 2016-03-31 | 2016-04-04 |  | ON GOING
| Capture and promote success stories: publish 16/yr. for the lead center; collect 4/yr./center | New Tool | Uses | Jim & Abby |  | Centers' stories due 2 in April, 2 in October --- shared eCenter, websites, SBA and ODSA | Success stories; | #1 - Leadership & Organizational | Jim is on track to release a new success story tool and then looking at
|  | 2016-03-15 | 2016-04-15 |  | ON GOING |  |  | Organizational | optimal ways to use the stories to promote the program
Review Meeting Schedule: |  |  | Status?
2016-03-15 | Status check & prepare update to the Network
2016-04-12 | Status check & prepare update to the Network
2016-05-17 | Status check & prepare update to the Network
2016-06-14 | Status check & prepare update to the Network
Values
Economic Impact – the reason for our existence
Service – the spirit with which we work
Guidance – the nature of our efforts
Collaboration – the openness we posess to work with others