## Enrich Quality of Services
| Where do we want to be? | Where are we now? | How will we get there?
Strategic Goal/ | Objectives | Current Status | Active Projects | Set Timeline | Goal Achieved/Measurable Result
1. Enrich Quality of Services | Systematic Collection of Client Data | Definitions and Standard Impact Survey Form set up. | 1. Review updated definitions on monthly conference | Complete
|  |  | 2. Review standard Impact Survey Form on monthly conference call | Complete
|  |  | 3. Deploy Clear Guidance and Training - Webinar | Complete
|  |  | 4. Monitor use in Center IC with attached documents monthly Impact Report. | Complete
|  | Refreshed in Fall of 2018 to comply with new SBA requirements. |  | Complete
| 2016 Update: Measure or Goal? |  | 4. Report out and review periodically | Complete | lead center AV2 improvement noticed- explore ways to quantify- (flagged file count?)
|  | Several centers still use a process a process to review client data year over year to calculate impact - This requires a higher lever of client review and management and meets attribution standards- is the process clear enough to meet AV2? | 5. Seek guidance on calculated impact utilized by OU, LCC, and Terra - | 2019-10-01
| Onboarding and Expectation Setting with Clients | Used by a few centers but not a uniform delivery model. | 1. Gather best practices currently used in specific centers | Complete
|  |  | 2. Create a standard intake process with clear directions and talking points | Complete
|  |  | 3. Review with directors on monthly conference call | Complete
|  |  | 4. Deploy across the network - Statewide Training | Complete
| Goal: See Survey - Increase response rate to 25% | FFY - Pivot - New metrics alignment - explore new opportunities to gather best practices that increase percentage of client's reporting impact | 5. See survey redevelopment below
| Update the Matrix of Specialists | Currently use Field Staff Expertise report. | 1. Send current list out for review and updating - 2 weeks turn-around in response | Complete
|  |  | 2. Share updated report and post in center | Complete
|  |  | 3. Report out and review periodically | Complete
4. Integrate into E Center
|  |  | 5. 2019 annual Update | 2019-06-01
| State Identify Funding to fill client needs with consultants (ex. HR) | Consultants available in some centers | 1. Using the Report in 1.c., create a list of gaps | Complete
|  |  | 2. Review with directors on monthly conference call | Complete
|  |  | 3. Through the process of identifying excess funds, identify consultants that are available to fill the gaps identified in 1.d.1. | Complete
|  | Pivot - Concept of a state pool of resource providers not easily aligned with local centers or deployable. Explore opportunities to regionalize or work with centers to implement strategies to fill local service gaps. | 4. Report out and review periodically | Complete
|  |  | 5.Brainstorm Ideas and concepts to share information | Complete
|  |  | 6. Launch as a component of Innovation Challenge - Annual redeployment of resources to meet gaps. | Complete
|  |  | 7. Operationalize | Complete
|  |  | 8. monitor | ongoing
| SBDC service centers should take a leadership role in helping their businesses have a strategic talent plan. | New Idea (paired with 4.j) | 1. Identify the current internship, and other learning-based programs/projects available in Ohio. | Complete
|  | PIVOT: Not aligned with stakeholder/client survey desired outcomes - Workforce development efforts in Ohio are numerous and complex - refocus on supporting Client needs/ align/train with Ohio Means Jobs | 2. Gather sample Strategic Talent Plans | Fall 2016
|  |  | 3. Formulate talking points to begin the discussions with agencies identified in 1.e.1 | Fall 2016
|  |  | 4. Identify key hosts or partners to help present the concept. | Fall 2016
|  |  | 5. Review with directors and prepare Train-the-Trainer opportunities | Winter/ Spring 2016
|  |  | 6. Report out and review periodically | Winter/ Spring 2016
|  | 2016 New Strategy | 2. Explore local partner opportunities with Ohio Means Jobs | Complete
|  |  | 3. Train network on Ohio Means Jobs - 1 stop opportunities/position description development tools etc. | Complete
|  |  | 4. Further training at Statewide 2017 | Complete
|  |  | 5. Provide network with relevant updates - annual meetings with OMJ | Complete
| Universal Onboarding Checklist: | No network consistency | 1. Review centers who have high rates of 641 compliance, survey feedback and impact | Complete
|  |  | 2. Develop a standard set of onboarding procedures | Complete | Better data, increased survey results
|  |  | 3. Deploy | Complete
|  |  | 4. Revisit in next strategic planning process | Summer/Fall 2019
| 1st Stop Revisions |  | Data and analysis | Complete
|  |  | Improve the customer interface - Streamline checklists- new branding | Complete
|  |  | Systematic Review of materials | Complete
|  |  | Review client needs - Aligned -Recommendations for new materials | Complete
|  |  | Focus group or new business input - | Complete
|  |  | Develop new 1st stop Guide | 1/2018 Delayed - External factors
|  |  | Develop Net Hire your First Guide | 1/1/2018 Delayed External Factors
|  | Oct 2018 -New Gateway launch drastically reduced SEO and visibility on the platform. | Launch first stop guide with multi-part hire your first webinar series | Jan/Spring/Summer 2017 -
|  |  | Explore opportunities to get analytic data - with new gateway | Delayed - External Factors - Review in Fall 2019
|  |  | Explore opportunities to get user feedback from 1st stop portion of gateway | Delayed - External Factors - Review in Fall 2019
|  |  | Explore path to integrate CSCC Nascent entrepreneur training with Gateway | Project dependent
| Improve Pre-Venture Client Management - Develop strategies for efficiency |  | Review historic client data | Complete
|  |  | 1. Review - review strategies and methodologies | Complete
|  |  | 2. Consider/ Data Review/Analytics third party Research? | DOA
|  |  | 3. Data analysis and Review | Complete
|  |  | 4.Educate Network - 2016 SBDC Statewide - State of SBDC | Complete
|  |  | 6. Explore - Best Practices - National Programs | Complete
|  |  | 7.Best Practice Training at Statewide 2017 | Complete
|  |  | 9. Explore/Brainstorm Online service delivery concepts- vet with network | Complete | Hours less than 35% in FFY 2018!
10 Best Practice sharing at Statewide 2018
|  |  | Monitor | ongoing
|  |  | 10. Innovation challenge funding to CSCC - | Delayed Possible launch Summer of 2019
11. Data Access - Empower centers through data access - See Dashboard development
|  |  | 12. Explore options to institutionalize CSCC ore Terra Model - | 2020 Strategic Plan
|  |  | 13. Directors meeting topic - require preventure training/online completion before access to advising service? Consider in person live webinars to centralize across state? Consider | 2020 Strategic Plan
| Manage - Black Hole Clients | Research has indicated an extremely large number of clients that utilize significant program resources with no visible impact attributed to the program. | 1. Further Analysis necessary? | Complete
| Goal: Reduce BHC by 1/2 by 2020 | PIVOT - Potential Impact Targets- | 2. Explore opportunities to generate awareness - Mid year/Year end report | Complete
|  | Se a goal - promote decline. | 3. Develop process - deploy | Complete
|  |  | 3. Integration in to Advisor Dashboard- | Partially accomplished - CIC is researching | FFY 2018 - PIT count and Hours Down significantly - not halved
|  |  | 4. Continued development with Center IC- is there a way to more easily | Spring 2019
|  |  | 5 Research segmentation within PITS | Spring 2019
|  |  | 6 Q 3 report | 2019-07-30
|  |  | 7.Strategic planning topic | Summer/Fall 2019
| Improve Client Survey Satisfaction Survey | The current survey is mailed out 90 days after an initial advising session. Look to bring the survey online. | 1. Explore options to take survey online | Complete
|  |  | 2. Launch Survey Monkey Version | Complete
|  |  | 3. Report Annual Results | Complete
|  |  | 4. Monitor | Complete
|  | PIVOT: Survey tools/process not compliant with ASBDC accreditation requirements. | Scrap old Survey
|  |  | 1. Reimagine Survey -Quick internal Brain Storm - Collect Best Practices -Engage Research? | Complete
|  |  | 2. Further Examine NPS Methodology | Complete
|  |  | 3. Evaluate Survey tools and path Forward - Automated? | Complete
|  |  | 4. Create policies and procedures | Complete
|  | Launch Executed - Instant great feedback | 5. Launch and operationalize | Complete
|  |  | 6.FFY 2016 Review | Complete
|  |  | 7. Make Redevelop messaging | Complete
|  |  | 8. FFY 2017 Review | Complete
|  | New Goal: 25% response Rate | 9. Explore strategies to Drive Response Rates - | Complete
|  |  | 10 Survey Revisions | Complete
|  |  | 11. FFY 2018 Review | Complete | Survey Goal Achieved 25.2% Response Rate!
|  |  | 12. Stake holder concerns that data is too good - Modify to capture feedback further in advising cycle | Complete
|  |  | 13. Explore concept to develop two separate surveys - One for new clients - process focused. One for LTCs content and expertise focused? | Fall /Winter 2019
|  |  | 14. Gather data for 2019 Strategic planning | Complete
|  |  | 15. New revisions/ relaunch changes | 2019-12-01
|  |  | 16. Train Field w/ refresher webinar on reviewing center and advisor level results | 2020-01-01
Generate a path forward for Former ITAC Directors
|  |  | 1. Create Export Lead | Complete
|  |  | 2. Export Summit | Complete
|  | Create goal? Exceed 500 clients in each year | 3. Export Branding and Identity | Complete
|  |  | 4. Develop a longer-term strategy | Complete
|  |  | 5. Map Services/barriers and opportunities - Gaps | Complete
|  |  | 6. Develop Cobranded - Marketing materials | Complete
|  |  | 7. Network Education - SBDC Export is an network promotion Task - Statewide | Complete | FFY 2018 - Exceeded 500 Clients
|  |  | 8. Explore new opportunities to incentivize centers to cross promote exports | Complete
|  |  | 9. FFY 2018 Monitoring | Complete | Fell below 500 - 489. Personnel issues WSU transition CSU transition.
|  |  | 10. Explore cross promotion activities with PTAC and MEP | Complete
|  |  | 11. MEP Statewide presentation | 2019-08-28
|  |  | 12 Fall/Winter pilot/ demonstration project | Fall winter 2019
|  |  | Explore opportunity for a statewide export summit (training and promotion) SBDC, SBA, Commerce, EXIM etc. | 2019-12-01

## Maximize Economic Impact
| Where do we want to be? | Where are we now? | How will we get there?
Strategic Goal | Objectives | Current Status | Active Projects | Set Timeline | Measure
2. Maximize Economic Impact | Consistent operation definition for HIC | Current definition exists | Review available Data - and trends - Has the HIC definition led to more impact? | Complete
|  | Pivot - Data revealed HIC client performance does not exceed standard existing client outcomes. | Review with network & Center Directors. | Complete
|  |  | Discuss metric restructuring to realign? | Complete
|  | REMOVE HIC from goal structure | FFY 2017 Metrics Restructure | Complete | FFY 2018 - Existing Business Hours exceed all other client segments!
|  |  | Monitor | ongoing
| Align HIC with other funding partners | Currently defined at the individual center level. | Using the ODSA BAC activities, we will create a standard intake process to ensure each center is connecting the business owner to all available programs as a referral for additional support. | Complete
|  | PIVOT: Data does not support | Research client data for insights | Complete
|  |  | Research Other State SBDC Programs for Insights - ILL, PA, FL, AL questioned for insights | Complete
|  |  | Operationalize Data - in metrics structure | Complete
Project placed on hold based on program analysis
| Foundation building partner roles | Currently defined at the individual center level. | 1. Gathering partner lists, roles, and inviting to ODSA BAC Regional meetings. | Complete
|  |  | 2. See ODSA BAC strategy Map | Complete
Oon Hold - Reprioritized
| Institutionalize Impact Form (80%) | Survey form in use about 20% centers | Quarter 1 Impact data files reviewed. All centers not using the new survey form have been notified (01/05/2016) it MUST implemented. | Complete
|  |  | Continue to review data and compliance monthly. | Complete
|  |  | Review other STATE Impact Policies | Complete
|  |  | Create flexible - Good Better Best Policy | Complete | Goal Achieved - 100% compliance
|  | New Project - Pilot impact collection Survey | explore a centralized annual survey? | Complete
| Center Accountability - Report Structure - Develop a reoccurring network wide report to identify center performance. | No clear reoccurring report sharing center impacts. General and | Develop report | Complete
|  |  | Field feedback | Complete
|  | PIVOT Spring 2016 - CARS reports require significant lead center resources to develop - Data Lags center performance. Feedback from the field and CIC library stats indicate the report is not viewed. | Deploy and Operationalize | complete
1.Review and brainstorm a path forward identify opportunities to create efficiencies in report generation.
|  |  | 2. Develop scorecard system - Goals at center level, individual advisor performance viewable. Contact other states on implementation | Complete
|  |  | 3. Launch and train the network 2016 Statewide | Complete
|  |  | 4. solicit feedback and improve. | Complete
|  |  | 5. Explore accountability process - Highlight underperforming centers? | Complete
|  |  | 6. Require performance self reporting in monthly narrative report - Include improvement plan. Work with underperformers on a case-by case basis | Complete
|  |  | 7. Operationalize | Complete
|  |  | 8. Explore opportunities to improve/develop more meaningful analytics and performance tools. | Complete
|  |  | 9. Collect best practices from - CIC Talk to FL SBDC | Complete
|  |  | 10. Pilot project/demonstration project | Complete
|  |  | 11. Develop Program Board, Center Board, Adviser Board and top performers/benchmarking board | Complete
|  |  | 12. Cross-Train Jay in board development | Complete
|  |  | 13. Launch boards - Webinar | Complete
|  |  | 14. monitor - Examine impact on 2019 metrics | ongoing
|  |  | 15. Share board insights on monthly calls | Complete
|  |  | 15. Solicit network feedback | Fall 2019
|  |  | 16. New board training | Fall/winter 2019
| Drive percent of clients reporting Impact to 30% | SBDC network has wild variances in % of clients reporting impact. Some centers as high as 40% bottom performer 4.8% . New goal for FFY 2017 - | 1. Launch New Goal | Complete
|  |  | 2.Best Practice Sharing in case management - Statewide panel | Complete
|  |  | 3. Share metrics at all network updates | Complete
|  |  | 4. Explore automation (See Survey Development) | Complete
|  |  | 5.2017 Outcomes | Complete
|  |  | 6. 2018 Outcomes | Complete | % dropped!
|  |  | 7. Adviser board integration | Complete
|  |  | 8. Revisit metric structure - align with preventure training requirement - Just focus on LTCs or align with broader client segmentation structure? | Summer/Fall 2019
| Develop Systematic Impact Review process | New state director found significant data integrity issues with reported 2015 impact. More than $200 million in impact was reported that does not align with impact reporting standards | 1. Leverage ASD group for best practices | Complete
|  |  | 2. Speak to Audit- What is an acceptable % of impact points to review | Complete
|  |  | 3. Test audit process process against full review of center | Complete
|  |  | 4. Create internal impact audit process | Complete
|  |  | 5. Compliance training for network | Complete | roughly $90 million of impact disallowed in FFY 2016
|  |  | 6. cross train staff and include full lead center team in review | Complete
|  |  | 7. further clarify | Complete
|  |  | 8. Review FFY 2017 | Complete | Significantly decrease in questioned costs difficult to quantify
|  |  | 9. review process for impact disallowance flagging - CIC solution | Complete | no current tool exists
|  |  | 10. Further refine process - Deploy mid year review | Complete
|  |  | 11. Review FFY 2018 | Complete | Significant increase in AV2 - One $7 million project not acceptable - Fewer than 40 disallowed impacts.
|  |  | 12. Further refine process - handoff to Diane | Complete
|  |  | 13. Review FFY 2018 | Complete
|  |  | 14. revisit possibility of flagging impact in CIC | Winter 2019
| Launch Center Assessment to Promote Excellence | Current reports only present data- consider developing a comprehensive center assessment to review performance, compare centers against similar centers/network averages, discuss local tactics to drive performance | 1. Map out cape concept | Complete
|  |  | 2. Explore best practices in the national network | Complete
|  |  | 3. Examine accreditation, follow up with FL, ID, | Complete
|  |  | 4. 1st draft | Complete
|  |  | 5. Test W/OSU Piketon | Complete
|  | CAPE was far to labor intensive - lack capacity to implement wholesale. | 6. Recap - Brainstorm opportunities to refine, revise and streamline | Complete
|  |  | 7. Explore opportunity to modularize - Onsite, Training, Performance and Alignment | Complete
|  |  | 8. Redevelop Modules | Complete
|  | Process further delayed - fall of 2018. Further evaluating options to move project forward. | 9. Train - lead center. Deploy onsite review and Training Review | Complete | 100% of centers reviewed in FFY 2019
|  |  | 10. Refine CAPE fiscal, Performance and alignment sections - Explore automation framework | 2019-05-01 | project delayed
| Implement universal data transparency |  | 11. Pilot | 2019-06-01
|  |  | 12. Train/ launch and Operationalize | Launch as part of closeout of FFY 2019 - Winter/Spring 2020
| MEET FAIR SHARE GOAL OF CAPITAL INFUSTION |  |  |  | 2016- Exceeded
2017- EXCEEDED - BEST YEAR IN PROGRAM HISTORY
2018- fell short - 300k
| EXCEED 2500 LTCs |  |  |  | 2016- Exceeded
2017- EXCEEDED
2018- Exceeded

## Strengthen Our Team
| Where do we want to be? | Where are we now? | How will we get there?
Strategic Goal | Objectives | Current Status | Active Projects | Set Timeline | Measure/Goal
3. Strengthen Our Team | Determine a Path forward for CBA - 100% network compliance | Team currently working - CBA In need of revision - Active partner may not interested in program renewal. | New Director review of CBA | Complete
DATA Evaluation - feedback- private sector interest?
|  | Toledo does not intend to partner in redevelopment | Urgent - Set vision forward for CBA- Committee recommendations - Chance to minimize cost | Urgent
|  |  | Research potential new partners - Explore licensing/profit share model | Complete
|  |  | research competative products | Complete
|  |  | Outreach to aligned institutions | Complete
|  |  | Host/legal channels - path forward | Complete
|  |  | Write/develop RFP | Complete
|  |  | Award to Kent | Complete
| Goal - CBA to be self sustaining - no lead center cost |  | Domini to project manage path forward | Complete
|  |  | CBA content review and marketing/messaging | Complete
|  |  | CBA Policy formation/registration with Kent | Complete
|  | one module launched - the rest by January | NEW CBA LAUNCH | Complete
|  |  | Inagural class review - solicit feedback | Complete
|  |  | Recommende changes - | Complete
|  |  | New HR module and accounting changes | Complete | GOAL Achieved - CBA Breaks EVEN
|  | partner slow to launch efforts | Market nationally | 2019-01-01
|  | Delay until fall break. | solicit feedback - recommend changes to Marketing test
|  |  | develop goals for moving CBA forward - Annual subscription - include in FFY 2020 Strat. Plan | Summer/fall 2019
| Knowledge - Are professional development opportunities sufficient to capture required knowledge base that has been identified? | Current tools available - CBA, Global Classroom, SBA, GrowthWheel, ProfitCents, IndustriousCFO (FINTEL), etc. | is there an action step here?
| Goal - Increase client survey -Advisor knowledege over three years. |  | Brainstorm Lead Center Webinar Opportunities - | Complete
|  |  | Align new opportunities to fill gaps identified through CBA revision | Complete
|  |  | Market reseach and Finance Training | Complete
|  |  | Ohio Bankers League research | Complete
|  |  | Bring Jeff Judy onboard | Complete
|  |  | Conduct commercial credit loan training | Complete
|  |  | Operationalize 4-6 annual webinars and one non-statewide seminar | Complete
| NEED - Add Strategy under Define statewide communication methodologies. Improve Comminication Channels. Improve communication to Need to identify process for internal communication to field and to stakeholders | Currently use email notifications, monthly conference calls and posting in eLibrary in Center IC. | Establish a field leadership system
Concept finalized- to field for comment
|  | New director - workforce survey shows that word is not getting out - backed up by 2016 statewide feedback from advisor group. | 1. Alternatives to SBDC Directors call | Complete
|  |  | 2. Pilot network webcast. | Complete
|  |  | 3. solicit feedback | Complete
|  |  | 4. operationalize | Complete
|  | Need for center to center communiation - Workforce survey | Launch field leadership team/system process | Complete
| Implement tools to promote engagement between centers and staff at various levels. | inter-center communication needs improvement. | Evaluate tools - Slack, linkedin etc. | Complete
|  |  | Test WorkPlace with SW Directors - feedback | Complete
|  |  | Pitch directors - preview to field | Complete
|  | New Goal 70% attainment | Launch Training and impleentation strategy | Complete
|  |  | Launch! | Complete | Goal Met - Exceeded 70%!
|  | New goal - daily lead center postings | monitor | Complete | 80% met
| Refine Workforce Survey | Current survey provides significant insight but is limited. Instinct tells us that workforce at certain SBDCs do not feel confident about the host relationship - it would be nice to explore this data further | Explore options for center level data - | Fall 2019
|  |  | Explore new tools for measuring Workforce perceptions/ Engagement - Q12 something else? | Fall 2019
| Launch Stakeholder Survey to solicit clear stakeholder observations about SBDC Program |  | review program history any formal process utilized
reach out to specific center directors for input
|  |  | Contact other SBDCs for best practies | Fall 2017 | Capacity issues - revisit nexy tear
| Establish orientation program | At one point the Ohio SBDC program had an orientation program - this traiing has not occurred for several years. Based on feedback, it is strongly needed. Use this as an opportunity to develop relationships, enphasize the SBC Strategic Palan and address common issues. | 1. Establish development process | Complete
|  |  | 2. run concept past CBA committee | Complete
|  |  | 3. pre-recorded webinar development | Complete
|  |  | 4. Develop additional content and learning objectives | Complete
|  |  | 5. Launch first orientation - specalized training for center Directors | Complete
|  |  | 6. Evaluate feedback | Complete
|  |  | 7. Operationalized - quarterly | Complete
|  |  | 8. Revisit | Complete
|  |  | 9. 2018 - re-evaluate and modify | Complete
|  | More CIC specific traingin requested | 10. Launch quarterly post orientation CIC webinars | Complete

## Enhance Visibility
| Where do we want to be? | Where are we now? | How will we get there?
Strategic Goal | Objectives | Current Status | Active Projects | Set Timeline
4. Enhance Visibility | Process for success stories. | No uniformity to the quality or content of success storises. Format under revision. submission process defined on Due Dates; internal review and release process underway. Field has given negative feedback about story process | 1. Status update - | Complete
|  |  | 2. Distribution List/strategy | Complete
|  | Hundreds of stories yield few usable results - how do we make this a meanginful process? | 3.Review past success story data- How many stories get used, how many stories submitted are usable? | Complete
|  | Is there a definable goal to measure quality of success stories? - Address in next strategic plannin session.? | 4. Develop strategy for Metrics - four quality stories per year | Complete
|  |  | 5. Explore opportunity to enhance consistency - and improve story Arch | Complete
|  | New 2018 Goal: 12 high quality stories developed and shared per year | 6. Meet with IT to discuss pat forward + Timeframe | Complete
|  |  | 7. Develop criteria | Complete
|  |  | 8. Build tool, train deploy and operatinalize | Complete
|  |  | 9. Training Webinar | complete
|  |  | 10. explore opportunities to align messaging with key strategic priorities - ED ourtreach | complete
|  |  | 11. Identify stakeholder aligned stores- Ohio SBDC bringing bankers and partners together. | complete |  | 2018 Goal Met - 12 stories
|  |  | 12. Re-develop portal | Spring 2019 | on-Hold
|  |  | 13. Re-imagine success story distribution - Opportunities to automate - Pitch to media, develop into a press package? | 2019-06-01
| New Objective: Success Story videos- Goal 3 per year | Stakeholders are interested in opportunities to developo/share content from programs. Leverage partner social media | 1.define project, process, scope and budget | complete
2. Identify story narrative and key messaging
3.Special request to field - seekin message aligned client success stories
|  |  | 4. Produce, edit, repeat. |  |  | 2018 Goal Met
5.Operationalize - Plan of 3 annually
|  |  | 6. Develop 2018 messaging prioritites |  |  | 2019 Goal Met
|  |  | 7. Develop 2019 Messaging | Maarch 2019
| Define stakeholder | Currently in Definitions. | 1. Define Stakeholder | Complete
|  | Pivot - Need strategy for ED and Bank Engagement | Add a secondary stakeholder definition - create program focus around ED/Bankers - rollout in 2017 RFP | Complete
| Traceability of stakeholder visits | process is indffective -look to alternative strategies to track/ monitor primary, secondary and collaborator outreach | Integrate into new monthly narrative reports | Complete
|  |  | Launch new monthly narrative reports w/stakeholder engegments included | Complete
|  |  | Wrap into CAPE Review | delayed pending launch of full CAPE
| Brand Guide creation (Year 2 -Brand uniformity; Year 3 -Brand improvement) | Current branding requirements are about 5 years old. Jim is working with ODSA Communications on update. Full guide is not necessary - create updated 1-pager. | 1. Develop Branding Guide | Complete
|  |  | 2. Develop interim guidance document | Complete
|  |  | 3. 1 Pager deployed | Complete
|  |  | 4. Integrate in onsite reviews, training reviews, and center visits - Included in CAPE and 888 training validation | Complete
|  |  | 5.Create comprehensive Branding, Communications and Messaging Guide | Complete
|  | on-hold pending discussion with state brand manager. Potential changes to state brand. Development leadership asked to hold project | 6. Review draft with Marketing and messaaging team | HOLD
|  |  | 7. Launch training Webinar | March, 2019
|  |  | 8. Deploy and monitor with CAPE integration | March, 2019
|  | New project :Create new identity for International Trade Assistance Centers (ITAC) | 1. Brainstorm topics and ideas with former ITAC team | Complete
|  |  | 2. New Logo - Statewide roll out of SBDC Export Assistance Network | Complete
|  |  | 3. Integrate Export assistance into all branding - 4pager and messaging | Complete
|  |  | 4. Crate new pop-up banners | Complete
|  |  | 5. regularly hilight in network updates. | Complete
| eCenter - Build and Launch | Current maintenance with Earl Gregorich's assistance. Plan for State Lead Center Staff to have training and begin the activities in FY2016 Q2. eCenter under review by ODSA. | reconveing planning committeee | Complete
|  |  | full review and cross training of lead center staff on back end | Complete
|  |  | re-brand- meet state branding guidelines | Complete
|  |  | Run internal checks - PIO, Deputy Chief, Chief | Complete
|  |  | Present to communications director/team | On Hold
develop rollout plan
Train the network - Hold in-persion training
rollout and launch
Press release and partner launches
establish ongoing metrics monitoring - process for reoccurring analytics
| h. Social media objective (possible additional objective under marketing)? | limited social media presence - Leverage state resources and collaborators. | ODSA Facebook page/Active on Twitter | Complete
|  |  | Explore opportunities for content calendar | Complete
|  |  | Develop monthly content calendar and knowledge articles for deployment | Complete
|  |  | Pilot | Complete
|  |  | Operationalize | On Hold
| Pivot |  | Explore opportunities for network to develop and share | On Hold
|  |  | Formalize content sharing with SBA District offices? | On Hold
|  |  | FFY 2020 Strategic plan | On Hold
|  |  | Survey field of personal and professional social media channels used by cneter | 2019-04-01
|  |  | Develop strategy to create echo chamber | May | On Hold
|  |  | Training at Ohio SBDC Statewide -buy in from linkedin group - Rollout | November | On Hold
|  |  | Develop process to monitor? | Novemvber
| Legislative outreach within the state (needed counterbalance to client visibility) | Ohio SBDC does not have a strong process of engagement with federal and satate legislators | Powermap key rleationships with key stakeholders (informal) | Complete
|  |  | Legerage local relationships - SW Ohio | Complete
|  |  | keep SW team informed | Complete
|  |  | explore DSA leagership engagement of Balderson | On Hold
|  | focus on host stakeholders or legislative (do local $ exist to draw down additional funds?) | On hold- see legislative engagement strategy map in development
| Recommend a strategic goal that calls for establishment of a statewide, centralized fundraising initiative that will benefit multiple regions. | New idea - see additional details | Canceled
| Create SBDC Marketing workgroup | Field put on noitce | 1. Assemble team | June 1,
|  | Pivot- Capacity issues - Project Based Approach | 2. Inventory materials/Socal Media use/need Asessment
3. New materials production
|  |  | 4. Bi weekly content calender with prepared tweets and Linkedin Posts - Pilot | Capacity concerns - Defer to strategic planning for path forward
ON HOLD
| Strategically align direct marketing with key impact generating client segments: Explore/ Leverage touchpoints for Existing Businesses in state government | As a governmen entitiy, are theere opportunities to leverage other ganncies as touchpoints for small business engagement, outreach, and marketing? Able to align with sttrategic priorities to engage more existing businesses. | 1. Meet with SOS | Complete
|  |  | 2. Meet with Commerce | Complete
|  |  | 3. Meet with JFS | Complete
|  |  | 4. Meet with AG | Complete
|  | Excellent meeting! | 5. Meet with BWC | Complete
|  |  | 6. Meet with AG | Complete
|  | SOS is revamping website to begin collecting contact information from business registrants - Can this align with segmentation strategy. BWC can share prospecting inofrmation of companies that are establishing a 1st time policy with BWC - Indicates existing business scaling up and hiring their first employees | 7. Prioritize follow up with SOS and BWC | Complete
|  |  | 8. BWC Followup | Complete
|  |  | 9. Research Follow up and process - Develop process for regular pulling and distribution of data. | Complete
|  |  | 10. Marketing and messaging team - Develop pitch and delivery model | Complete
|  |  | 12. Develop marketing piece - Constant contact | 2019-01-01
|  | Goal: 20% growth in new (not retained) existing business clients | 13. Deploy and oprerationalize | Spring -2019
| Engage Top Referrers - ED and Bank Outreach | Early FFY 2017 data analysis shows clear evidance that the referrers of SBDC's top clients are Banks and the economic development community. Leverage these relationships - expand reach through education of thsese secondary stakeholders. | Data Analysis - furtther revision
|  |  | Share data at FFY 2016 Statewide - | Complete
|  |  | Collect best practices - from other states | Complete
|  |  | Create focus area as part fo RFP process - include in marketing plans | Complete
|  | ED 2017, Banks 2018 - Maintenance in 2019 | Establish strategy and needs | Complete
|  |  | establish reporting criteria - Include in monthly report | Complete
|  |  | Share data at FFY 2016 Statewide - | Complete
|  |  | require centers to develop a marketing and engagemetn plan to guide efforts | Complete
|  |  | Explore opportunities to engage OEDA | Complete
| Relaunch Marketing materials 2019 |  | Newsletter - monthly participatin | Complete
|  |  | OEDA Annual Conference - Work with ODSA leadership -gain approval to present | Complete
|  |  | Community Development/ Mainstreet redevelopment success story | Complete
|  |  | OEDA presenation | Complete
|  |  | Monitor center engagement of ED community -via monthly reports | Complete
|  | need for bank specific marketing materials | Search other programs for best practices | Complete
|  |  | R& D from LA SBDC - develop bank pocketcard | Complete
|  |  | Mail to community bankers association | Complete
develop success story video with crossover messaging with Banker-
|  |  | Deploy at bankers day | ODSA not on Agenda
|  |  | future consideration - banker partner on SBDC advisory board? | Summer/fall 2019
|  |  | SBDC inclusion in OEDA basic ED training. | revisit in strategic planning